## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Blockchain (Web3)
INTERN NAME: | Sheefa Jalali
PROJECT NAME: | Blockchain Based Authentication
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2023-09-20
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Blockchain Based Authentication
PROJECT ID | IP23-001275
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Harshada Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 14th August 2023 | Smart Contract Integration Challenge | Technical | Smart contract integration complexities identified during development | Conduct a thorough analysis of smart contract integration before development | Implemented additional unit testing and refactored contract structure | Sheefa Jalali | Closed | Integration challenges were resolved with the recommended actions.
2 | 23rd August 2023 | Performance Degradation during Heavy Load | Performance | Increased response times observed during simulated heavy load testing | Optimize smart contract code and system architecture for improved performance | Integration challenges were resolved with the recommended actions. | Sheefa Jalali | Closed | Performance improved significantly after optimizations.
3 | 5th September 2023 | Security Vulnerability in Hash Generation | Security | Potential vulnerability in the hash generation algorithm | Enhance the hashing algorithm and conduct a security review | Revised and strengthened the hash generation algorithm | Sheefa Jalali | Closed | Security risk mitigated with algorithm enhancement and rigorous testing.
4 | 15th September 2023 | User Experience Feedback | User Experience | Users reported difficulty in understanding the login process | Enhance user interface and provide clearer instructions | Updated UI/UX design and included detailed login instructions | Sheefa Jalali | Closed | Positive feedback received post UI enhancements.